NETCOMPLEX

Migration Progress Review

Repo audit — April 2026  |  Compared against: netcomplex-migration-plan.docx v1

# Executive Summary

This report compares the current repository state against the NetComplex multi-tenant migration plan. The tree was diffed against both the previous snapshot (original review) and the updated migration plan to identify progress, variances, and open risks.

| 8 Items completed | 4 In progress | 5 Open gaps | 2 Deferred (correct) |
| --- | --- | --- | --- |

Overall Assessment Good momentum. The structural work from Phases 0-2 progressed quickly — route group separation, tenant/ component folder, lib/tenant/ expansion, and admin scaffolding are all in. The two remaining critical blockers before a second tenant can be onboarded are API route enforcement (withTenant() not yet applied to 35+ routes) and CSS variable wiring to the DB.

# Phase 0 — Foundation

| Task / Item | Status | Notes |
| --- | --- | --- |
| LOCAL_TENANT_SLUG env var | ✗ Open | Not visible in the tree. No .env.local committed (expected), but not referenced in AGENTS.md or README. Verify this is set in all dev environments before any Soralia work continues. |
| withTenant() helper | ✓ Done | src/lib/tenant/with-tenant.ts created — exactly as specified. lib/tenant/ is now a proper folder. |
| lib/tenant/context.tsx | ✓ Done | Added alongside with-tenant.ts. Server + React context helpers are in place. |
| Soralia seeded as tenant #1 | ~ Partial | scripts/backfill-tenant-records.ts is new and covers the data migration requirement. However, no seed that creates Soralia as the canonical tenant #1 with branding values (logo, colors) is visible. |
| TierGuard vs FeatureGate decision | ~ Partial | FeatureGate.tsx was created in components/tenant/. TierGuard.tsx still exists in components/ui/. Both now coexist with no documented scope boundary — this needs a decision and a comment in each file. |
| /admin/platform/ vs /platform/ decision | ✓ Done | Resolved cleanly via the new (platform) route group containing home, pricing, login, and signup pages. NetComplex marketing surface is now clearly separated from tenant app routes. |

# Phase 1 — Enforcement

Critical: Both items below are blockers for second-tenant onboarding API route enforcement and dynamic branding must be complete before any tenant other than Soralia Village is activated on the platform. Data leakage between tenants is a critical incident.

| Task / Item | Status | Notes |
| --- | --- | --- |
| API route tenant enforcement | ✗ Open | 35+ routes under src/app/api/ remain unscoped. withTenant() helper was created but appears not yet applied to individual route handlers. Every route must call withTenant() first and pass the resolved tenantId to all Drizzle queries. |
| CSS vars wired to tenant DB | ✗ Open | TenantStyles.tsx was moved to components/tenant/ but no new DB-wiring code is visible from the tree. Dynamic branding (primaryColor, accentColor, logoUrl pulled from the tenants table) appears to still be pending. |
| TenantProvider + TenantStyles moved | ✓ Done | Both now live in src/components/tenant/ alongside FeatureGate.tsx. The tenant/ component folder is correctly established. |
| Locale file consolidation | ✗ Open | Duplication persists: public/locales/ (af/en/xh/zu) and src/app/[lng]/locales/ (af/en/xh/zu) both still present. Must be resolved before multi-tenant i18n or per-tenant translation overrides are considered. |
| FeatureGate applied to routes | ~ Partial | FeatureGate.tsx component created. No evidence yet of it being applied to individual page routes or nav items — the wrapping step is still pending. |

# Phase 2 — Admin UI & Tenant Tooling

| Task / Item | Status | Notes |
| --- | --- | --- |
| Tenant admin UI — edit & features | ✓ Done | (platform)/admin/platform/[id]/edit/ and /features/ pages added, each with a components.tsx. Full CRUD for tenants is now scaffolded. |
| tenantId backfill script | ✓ Done | scripts/backfill-tenant-records.ts is new and covers the data migration requirement for existing rows. |
| Migration: make tenantId nullable | ✓ Done | New migration 20260406_make_better_auth_tenantid_nullable applied. Pragmatic move that allows the backfill to run without breaking existing rows. |
| (platform) route group | ✓ Done | src/app/(platform)/ created with home, pricing, login, and signup pages plus a shared layout.tsx. NetComplex marketing surface is now a first-class route group. |
| (tenant) route group | ✓ Done | All tenant-scoped admin routes moved under (tenant)/ with its own layout.tsx. Clean separation from platform-level admin is achieved. |
| tenantFeatures.tsx | ✓ Done | src/lib/features/tenantFeatures.tsx created. Per-tenant feature config now sits alongside the existing feature registry. |
| Component registry (registry.ts) | ✗ Open | No src/components/registry.ts visible in the tree. WidgetRenderer is not yet wired to a central component registry. |
| components/custom/ + CustomSectionRenderer | ✗ Open | No custom/ folder created yet. The bespoke slot pattern for tenant-specific content sections has not been started. |

# Phases 3 & 4 — Correctly Deferred

| Task / Item | Status | Notes |
| --- | --- | --- |
| Second tenant onboarding | — Deferred | Not started. Correctly deferred — Phase 1 enforcement (API scoping + CSS vars) must be complete first. |
| [lng] page migration | — Deferred | src/app/[lng]/layout.tsx exists but no application pages have moved. Correctly deferred — this is the highest-risk change and stays last. |

# New Additions Not in the Plan

The following files and folders appeared in the current tree that were not present in the original snapshot and are not covered by the migration plan.

## demo-site/

A static HTML/JS demo site was added covering conservation, dashboard, directory, services, and other pages. This is a meaningful body of work outside the migration plan.

Action required Clarify the intent: is this a sales tool for prospective NetComplex clients, a design prototype, or something else? If it is a sales/pitch tool it should be tracked and maintained deliberately — it will go stale as the real platform evolves. Assign an owner.

## docs/ folder — significant expansion

| NETCOMPLEX_ARCHITECTURE.md | New high-level architecture doc |
| --- | --- |
| NETCOMPLEX_PLAN.md | New plan document |
| MULTI_TENANT.md + MULTI_TENANT_SIGNUP.md | Multi-tenant design docs |
| TENANT_AUDIT.md | Tenant audit reference |
| WHITE_LABEL_MIGRATE.md | White-label migration notes |
| netcomplex_migration_planV0.md + v1.md | Versioned plan iterations |
| Netcomplex-migration-plan.docx (in docs/) | The living plan document |

Good for team alignment. However, multiple versioned plan documents (V0, v1, XML, docx) risk divergence. Treat the .docx as the single source of truth going forward and remove or archive the markdown iterations.

## src/proxy.ts at src/ root

A new src/proxy.ts appeared alongside the existing src/app/proxy.ts. Two proxy files in different locations is a risk — confirm which is active and remove the other.

## opencode.json

AI coding assistant config at the root. Acceptable — verify that no sensitive context (DB credentials, tenant slugs, API keys) is baked into it.

## justfile

Task runner added to the root. Good practice for discoverability. Ensure that migration-critical tasks (backfill, seed, tenant setup, withTenant() audit) are wired into it so the whole team can run them without digging through scripts/.

# Priority Actions — What to Do Next

## Immediate (before any other work)

- Confirm LOCAL_TENANT_SLUG=soralia-village is set in every developer's .env.local and document it in AGENTS.md.

- Audit all 35+ API routes and apply withTenant() to each handler as the first operation — no exceptions.

- Wire TenantStyles.tsx to pull primaryColor, accentColor, and logoUrl dynamically from the tenants table.

## This week

- Document the TierGuard vs FeatureGate scope boundary in each file's header comment.

- Apply FeatureGate to at least the top-level nav items and major route layouts.

- Consolidate locale files: pick public/locales/ or src/app/[lng]/locales/ as the canonical location and delete the duplicate set.

- Create a seed entry for Soralia Village as tenant #1 with real branding values committed.

## Next 1–2 weeks

- Create src/components/registry.ts and wire WidgetRenderer to it.

- Clarify and document the purpose of demo-site/.

- Investigate and resolve the dual proxy.ts situation.

- Wire migration tasks into the justfile so they are discoverable.

## Do not start yet

- Second tenant onboarding — API enforcement and dynamic branding must be done first.

- [lng] route migration — stays last; deferred correctly.

NetComplex Migration Progress Review  •  April 2026  •  Internal Use Only